## LEP Checklist
#VALUE! |  |  | Program coordinator planning checklist
- Update your start date - Dates below will automatically with suggested minimum timeframes - Overwrite these as required |  | Program Start Date | 2025-01-06 | P | Type 'P' = complete (must be capital P)
Not complete
# | Checklist | Date Due | Person Responsible | Status | Comments
1 | Administration
1.1 | Confirm through your approvals process and return signed agreement to LSV | 2024-08-19 |  |  | Ensure your insurance policies include staff and children participating off-site if relevant.
1.2 | Confirm your budget (including pricing structure) | 2024-08-19 |  |  | Update as required (ongoing). Contact LSV for recomended pricing. - Recommend offering subsidised program fee (i.e. concession card holders, discounts through targeted community groups etc.)
1.3 | Apply for funding (if required) | 2024-08-09 |  |  | - See grant application checklist for further detail - Check whether the program can go ahead without funding - Check funding dates (outcome and expected delivery) match your program timelines
1.4 | Complete induction with LSV's Education Team | 2024-08-09 |  |  | In this induction we can talk through: - tasks (i.e., this checklist) - program resources - organise regular check-ins to ensure you have the level of support you need
1.5 | Confirm program details with LSV Education Team | 2024-09-28 |  |  | This will have been discussed prior to the written agreement. Please check that LSV has the details of your program including: - delivery mode/s you are offering (i.e. holiday, schools, community groups, etc.) - Program dates, time/s, session length/s and expeceted numbers
1.6 | Order required equipment and resources | 2024-09-28 |  |  | See 'Equipment List' for further information.
1.7 | Order required rash vests and nipper caps (as applicable) | 2024-08-19
1.8 | Return any borrowed/hired equipment | 2025-01-10
1.1 | Report to LSV participant numbers and any relevant feedback | 2025-01-20
1.11 | Organise Victorian Water Safety Certificate for all participants that meet requirements | 2025-01-09
1.12 | Organise LEP certificate for all participants | 2025-01-09
2 | Safety
2.1 | Organise LSV Education location assessment | 2024-09-28 |  |  | LSV's Education Team will confirm through an internal assessment process, with your support, if a location is suitable for LEP program delivery.
2.2 | Obtain relevant permits for venue | 2024-10-08 |  |  | It is your responsibility to check legal requirements for use of the location including obtaining permits - LSV can support you in this process.
2.3 | Risk assessment policies and procedures developed/updated | 2024-11-17 |  |  | Ongoing, include communication and access for emergency services personnel.
2.4 | Have required risk documentation available for Team Leader | 2025-01-03
2.5 | Have participant groups and staff details available for Team Leader | 2025-01-03
3 | Staff Management
3.1 | Start recruiting your staff | 2024-09-08 |  |  | Ensure prospective staff members know the dates and training requirements well ahead of time.
3.2 | Confirm LSV program support required for program | 2024-09-28 |  |  | LSV will commit 2x staff for first year programs, any additional support required must be communicated as soon as possible.
3.3 | Organise dates for Program Training and additional Award Training (as required) | 2024-09-28 |  |  | See your 'Program Coordinator Guide' for required qualifications depending on the program location type. Include in permit application (if required) and ensure a training room is available.
3.4 | Order staff uniforms (as required) | 2024-11-07 |  |  | For outdoor programs, ensure they are SunSmart (long sleeve, wide brimmed hat), see the 'Program Coordinator Guide' for further detail.
3.5 | Have staff complete online training | 2024-12-23 |  |  | Training can be completed online in their own time or a time set by you and must be completed prior to any practical training.
3.6 | Provide staff with program details | 2024-12-30
3.7 | Staff training delivered | 2024-12-30
4 | Programming
4.1 | Contact your local Traditional Owners | 2024-09-08 |  |  | See 'Program Coordinator Guide' for supporting information.
4.2 | Confirm process for getting equipment to and from the venue/storing securely | 2024-11-17 |  |  | Book trailers/cars as required.
4.3 | Group participants (age and ability) | 2024-12-27 |  |  | - Ongoing until close of enrolment - Ensure you have enough support for participant requirements
4.4 | Plan for any accessibiilty needs for any participants and/or their guardian/carer | 2024-11-07 |  |  | - Ongoing
4.5 | Conduct skills assessments with those outside your programs/lessons | 2024-12-27 |  |  | Allow time to source any additional support required.
5 | Marketing
5.1 | Develop media & communications plan and start marketing - see Resource Hub for various templates, logos, etc. | 2024-09-28 |  |  | Ensure everyone who needs to know has the required information - i.e., CSOs. Allow plenty of time for approvals and provide schools with material before end of terms. Check any funding body/sponsorship acknowledgement requirements.
5.2 | Set up website/'Participants Enrolment' form including terms and conditions | 2024-10-07 |  |  | Ensure payment taken on enrolment.
5.3 | Send website/ registration link to LSV to update LSV page | 2024-10-07
5.4 | Provide participants with further program information | 2024-12-23 |  |  | If not already sent as the enrolments are confirmed.
5.5 | Confirm program schedule based on numbers/age & ability groups | 2024-12-30
5.6 | Reminder email sent to participants | 2025-01-01
5.7 | Take photos/video - ensure you have Media Consent | 2025-01-06
5.8 | Follow-up contact with all participants | 2025-01-10
6 | Evaluation
6.1 | Establish any evaluation requirements | 2024-08-19
6.2 | Conduct evaluation (surveys, skills tests, as required) | 2025-01-06
6.3 | Complete evaluation and disseminate to relevant parties | 2025-02-05 |  |  | Internal and/or funding body requirement
This checklist is a guide only from Life Saving Victoria (LSV) in conjunction with the Lifesaving Education Program (LEP) Guide and does not need to be returned to LSV.