## Timeline snapshot
Oct 7
  Websites live: share with LSV
Oct 7
  Register with local ‘What’s On’ entities
Oct 7
Notify other key groups
Nov 18
LSV announce holiday programs
Nov 18
On share and announce registrations open
Nov 18
  Emails to database, past participants, schools
Nov 18
  Print and display posters
Nov 18
Share digital assets
Nov 25
Share media release with local media
Nov 25
Commence weekly social media post
Dec 1
  LSV announce Water Safety Month/ join a program near you
Dec 4
  Commence weekly updates on enrolments
Dec 6
LSV social media post
Dec 13
LSV social media post
December
Other opportunities depending on uptake

## Key Actions
Key actions
Timing | Action/What | Audience | Channel/s | Responsibility | Complete (yes / no)
w/c 7/10 | WEBSITES LIVE: - Partner websites updated with details/dates - Partners to provide LSV with program dates and partner logos | Local community (incl Local schools, current swim school families) | Websites | Partners | No
w/c 7/10 | LSV update LEP webpage with links to partner programs | State-wide audience, holiday makers |  | LSV | No
w/c 7/10 | NOTIFY STAKEHOLDERS EARLY - share program dates and details with key local promo partners to agree and secure promotional activity/listings (eg.) - register the program on Council 'What's On" - list program dates on local newsletters, Local Publications/ Websites/Digital listings, local online calendars | Local community | phone/email/f-2-f | Partners | No
w/c 18/11 | Announce LEP Holiday programs open for bookings. | local community & holiday makers | Social Media channels | ALL | No
w/c 18/11 | Add email signature to key staff members emails | All acquaintences (past participants, local stakeholders and influencers) | Emails | ALL | No
w/c 18/11 | SEND BOOKINGS OPEN EMAIL: - email local schools to share program details with parents | Parents of local school students | For inclusion in school newsletters Email &/or newsletter | Partners | No
| - email database of previous participants | Past LEP participants | Email &/or newsletter | Partners | No
| - email database to announce bookings are open | Current swim school families, students on waitlists | Email &/or newsletter | Partners | No
w/c 18/11 | DISTRIBUTE PROGRAM PROMOTIONAL MATERIAL: - Print and distribute/display promo posters in key/ high profile locations physical locations - Send out digital assets/promo posters to key locations that have digital display capacity | Local Community and visiting holiday makers | Suggested locations: Around your aquatic centre, Community Centres, Tourist Info Boards, Resort and Camping grounds, Libraries, Supermarkets | Partners | No
w/c 25/11 | DISTRIBUTE MEDIA RELEASE: - LSV have created an editable Media release which partners can update to include partner information prior to sharing with local media | Regional and adjacent community members | Digital, Radio and/or Print | Partners | No
w/c 25/11 | Begin weeekly social media posts | Local community | Social Media channels including local Facebook community groups | Partners | No
1st Dec | Social media post: December is Water Safety Month | Local Community | Social Media channels | ALL | No
w/c 2/12 | Weekly Partner Check-in commence. Share enrolments and any media opportunities with LSV. | Partners | Phone/ email | LSV | No
w/c 2/12 | LSV share bookings open in School Swimming and Water Safety Newsletter | State-wide audience- LSV school database | Email | LSV | No
w/c 9/12 | Social media post | Local Community | Social Media channels including local Facebook community groups | ALL | No
During/ after local LEP completed | Partners to share activity photos or LEP shout out on social media and tag LSV | Local community | Social Media | Partner | No
After local LEP completed | LSV to on-share partner content to our social platforms | State-wide audience | Social media | LSV | No
Mid Jan 2024 | Post campaign reflection | Internal & with partners | Feedback, review results and engagement | LSV in conjunction with partners | No
End Jan/beg Feb | LSV to publicise an end of campaign article and circulate via LSV eNews | State-wide audience (distribution numbers TBC) | email | LSV | No

## Optional suggestions
Optional ideas to promote the program
Timing | Action/What | Audience | Channel/s | Responsibility | Examples
September | Speak with local Indigenous group/s, CALD group/s, Scouts etc. early to discuss opportunities for promoting with them (consider providing subsidised fee for particular groups and promoting) | Local community (particularly minority and disadvantaged groups) | As available - face to face, phone, email | Partner
October | Sponsorship/s through local businesses | Local community/ holiday makers | As available - face to face, phone, email | Partner | Example - Sposorship proposal example.docx
October | Share with other user groups of local waterway (i.e., swimming club, stand-up paddle board/ paddle boat, hire companies etc.) | Local community/ holiday makers | As available - face to face, phone, email | Partner
October | Book additional sessions/ days with local holiday program providers/ Scouts / other community groups. | Local community | As available - face to face, phone, email | Partner
November | Work with library on Water Safety month activity/ies and program promotion (i.e. storytime with a lifeguard) | Local community | As available - face to face, phone, email | Partner | World Drowning Prevention Day Suggested Reading and Activities
November | Church, local business, other community groups newsletters | Local community/ holiday makers | Email | Partner
November | Specific posts (i.e. local photos/ stories) to community FB groups | Local community | Social media | Partner
November/ December | TikTok / short videos from previous programs | Local community/ holiday makers | Social media | Partner
December/ January | Come and Try Day - could tie in with LSV training dates | Local community | Face to face | Partner

## Contingency Planning
Additional actions if bookings are low (mid-Dec)
Timing | Action/What | Audience | Channel/s | Responsibility
To be agreed for each location | Holiday program bookings closing soon | Tailored to local region | Channels and timing to be agreed based on location and enrolments | LSV & Partners
Timing depenent on initial interest/uptake | Media coverage via Local paper / digital media outlets | Regional Community | Digital (tbc if printed) | Partner led (confirm details with LSV before sending)
Timing depenent on initial interest/uptake | Radio Media coverage via Regional /Syndicated Radio stations | Regional Community | Radio | Partner led (confirm details with LSV before sending)
Timing depenent on initial interest/uptake | TV Media coverage via ABC News/ WIN TV | Regional Community | TV | Partner led (confirm details with LSV before sending)